## Slide 1: AuthClaw architecture execution plan
Verified repository status
Three engineers • one coordinated migration
PROJECT STATUS • EXECUTION PLAN
Notes: [Sources]
- Requested Simple Dark Mode template: retained reference.pptx
- docs/AUTHCLAW_ARCHITECTURE_PARALLEL_IMPLEMENTATION_PLAN.md

## Slide 2: The target architecture is not implemented yet
Data
Backend and agent use separately provisioned PostgreSQL databases.
Network
One NAT per regional stack; no AWS service VPC endpoints.
Compute
Fargate only; no Graviton provider or ARM64 runtime.
Verified status
Current infrastructure remains Fargate-based, service-separated, NAT-routed, and backed by two PostgreSQL databases.
Python runtime dependencies have ARM64 wheels, but CI and ECS are not ARM64-ready.
Notes: [Sources]
- infra/terraform/modules/regional_stack/main.tf
- .github/workflows/ci.yml
- docker-compose.full.yml

## Slide 3: Four assumptions in the architecture document must be corrected
Graviton scope
Incorrect: ARM builds and ECS EC2 infrastructure are required.
ECR lifecycle
Outdated: repositories already retain the latest 30 images.
Latency baseline
Unsupported: no committed measured baseline proves the claim.
Two databases
Unproven: separation is deliberate in Compose and Terraform.
Repository corrections
These statements are outdated, incorrect, or unsupported by committed evidence.
Notes: [Sources]
- infra/terraform/registry.tf
- infra/terraform/modules/regional_stack/main.tf
- .github/workflows/ci.yml
- script/gateway_latency_benchmark.py

## Slide 4: The agreed data target is one PostgreSQL instance with isolated ownership
Backend database / schema
Dedicated backend role
Independent migrations
Tenant-safe pooling
Agent database / schema
Dedicated agent role
Independent migrations
No backend data access
Non-negotiable target
Backend and agent share one PostgreSQL instance—not tables, credentials, or unrestricted permissions.
Prefer separate databases inside the instance unless cross-schema queries are required.
Notes: [Sources]
- infra/terraform/modules/regional_stack/main.tf
- backend/app/db/session.py
- services/agent/database/__init__.py

## Slide 5: Record one shared baseline and give the same evidence to every engineer
Runtime performance
Gateway p50/p95/p99 for plain, redacted, and streaming paths.
Service capacity
CPU and memory p95/peaks, task limits, and container image sizes.
Data and audit
Database size/connections, pool behavior, event rate, lag, and replay time.
Cloud and rollback
NAT traffic/cost plus deployed and rollback image digests.
Notes: [Sources]
- script/gateway_latency_benchmark.py
- docs/AUTHCLAW_ARCHITECTURE_PARALLEL_IMPLEMENTATION_PLAN.md

## Slide 6: Ownership is clear; the baseline is shared
Engineer 1 — Platform ARM64 • Graviton • endpoints • ECR
Engineer 2 — Data PostgreSQL • migration • isolation • audit
Engineer 3 — Runtime Sidecars • isolation • benchmarks
Notes: [Sources]
- docs/AUTHCLAW_ARCHITECTURE_PARALLEL_IMPLEMENTATION_PLAN.md

## Slide 7: Three workstreams proceed in parallel after the baseline is approved
Build ARM64 images; add Graviton capacity and VPC endpoints.
Platform workstream
Rehearse one-instance migration, permissions, validation, and rollback.
Database workstream
Co-locate gateway sidecars on Fargate before moving compute.
Runtime workstream
Protect digests; add SBOM, signing, task roles, and runtime controls.
Hardening workstream
Parallel delivery
Engineer 1 owns shared Terraform, CI, and deployment workflows.
Engineers 2 and 3 supply infrastructure requirements without editing the same stack concurrently.
Notes: [Sources]
- docs/AUTHCLAW_ARCHITECTURE_PARALLEL_IMPLEMENTATION_PLAN.md
- infra/terraform/modules/regional_stack/main.tf

## Slide 8: Parallel engineering does not mean a big-bang production release
Release one variable at a time Every production change needs a measured acceptance gate and tested rollback.
1 Baseline approved
Start with evidence and reversible foundations. Co-location is validated on Fargate before Graviton, and database consolidation is released separately from compute and audit transport changes.
Do not reduce image retention until deployed and rollback digests are protected.
2 ARM64 builds + endpoints
3 Fargate sidecar task
4 Graviton canaries
5 PostgreSQL cutover
Notes: [Sources]
- docs/AUTHCLAW_ARCHITECTURE_PARALLEL_IMPLEMENTATION_PLAN.md
- .github/workflows/deploy-controlled-beta.yml

## Slide 9: Compute and data changes are accepted only after four concrete gates pass
Fargate rollback
The previous compute path remains tested and recoverable.
ARM64 runtime
Every image builds and passes health checks on Graviton.
Tenant isolation
A real pooled tenant A → tenant B reuse test passes.
Shared database
Both migration sets complete and data validation matches.
Acceptance gates — compute and data
A successful deployment is not enough; behavior, isolation, and rollback must be demonstrated.
Notes: [Sources]
- backend/tests/test_tenant_session_context.py
- backend/app/db/session.py
- services/agent/database/__init__.py
- .github/workflows/ci.yml

## Slide 10: Four final gates complete the definition of done
Private sidecars
OPA and Presidio cannot be reached from another ECS task.
Performance
Plain, redacted, and streaming requests meet agreed budgets.
Audit integrity
Ordering, dedupe, replay, DLQ, and fallback tests pass.
Safe retention
Lifecycle cleanup preserves deployed and rollback digests.
Notes: [Sources]
- gateway/policy.go
- gateway/redact.go
- audit_consumer/consumer.py
- infra/clickhouse/init.sql
- infra/terraform/registry.tf

## Slide 11: Approve the shared baseline, then start the three workstreams.
NEXT ACTION
AUTHCLAW • THREE ENGINEERS
Notes: [Sources]
- docs/AUTHCLAW_ARCHITECTURE_PARALLEL_IMPLEMENTATION_PLAN.md